## Slide 1
KFCA Corporate Strategy
Seed Data — 3 Pillars + 6 Enablers
100 Projects · 965 Milestones · 42 KPIs · All with Exact Dates
STRATEGIC PILLARS
Board-level strategic themes.
Define WHAT KFCA delivers.
• Customer Experience
• Assets & Infrastructure
• Commercialization
3 pillars · 9 initiatives · 40 projects
ENABLERS
Cross-cutting capabilities.
Define HOW KFCA delivers.
• Governance & Steering • Op. Excellence
• Technology & Innovation • Capabilities Building
• Branding & Social • PS Participation & Funding
6 enablers · 17 initiatives · 60 projects

## Slide 2
Programme Structure — Pillars vs Enablers
Type | Name | Initiatives | Projects | Database
PILLAR | Customer Experience | 2 | 7 | spmo_pillars (pillar_type='pillar')
PILLAR | Assets & Infrastructure | 4 | 24 | spmo_pillars (pillar_type='pillar')
PILLAR | Commercialization | 3 | 10 | spmo_pillars (pillar_type='pillar')
ENABLER | Governance & Steering | 3 | 15 | spmo_pillars (pillar_type='enabler')
ENABLER | Operational Excellence | 3 | 8 | spmo_pillars (pillar_type='enabler')
ENABLER | Technology & Innovation | 5 | 20 | spmo_pillars (pillar_type='enabler')
ENABLER | Capabilities Building | 2 | 8 | spmo_pillars (pillar_type='enabler')
ENABLER | Branding & Social Contribution | 2 | 3 | spmo_pillars (pillar_type='enabler')
ENABLER | PS Participation & Funding | 2 | 2 | spmo_pillars (pillar_type='enabler')
 | TOTAL | 26 | 100 | All in spmo_pillars with pillar_type column
Key Design Decision: Both pillars and enablers are stored in the same spmo_pillars table. A pillar_type column ('pillar' or 'enabler') distinguishes them. The computation engine treats them identically — progress cascades the same way. The only difference is visual: the dashboard groups pillars separately from enablers, and the strategy map shows pillars as main columns with enablers as a supporting row below.
KFCA Seed Data (Pillars & Enablers) · Page 2

## Slide 3
PILLAR
Assets and infrastructure — 22 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P1 | Meet iRAP requirements | Operations and M | O. Aldahash | 2023-11-22 | 2024-08-18 | Completed | 100% | 25% | Completed on t
P2 | Automated equipment coverage (CCTV) | Technology and D | B. Alruwaili | 2023-10-10 | 2025-09-13 | Completed | 100% | 25% | Completed on t
P5 | Cargo journey optimization | Projects | A. Bumteia | 2023-12-15 | 2026-05-15 | Execution | 82% | 25% | Delayed
P6 | Road assessment technologies | Operations and M | F. Yusuf | 2023-11-29 | 2025-07-17 | Completed | 100% | 25% | Completed on t
P7 | Road and Facility Asset Management | Technology and D | M. Albutery | 2024-08-08 | 2025-07-17 | Completed | 100% | 60% | Completed with
P9 | Traffic monitoring and forecasting | Strategy and Ena | TBD | 2026-07-01 | 2026-07-01 | Not Started | 0% | 40% | Not started
P10A | Enhancement of terminals & access | Projects | M. Salmeen | 2023-12-10 | 2024-08-28 | Completed | 100% | 8% | Completed on t
P10B | Enhancement of customer terminals & | Projects | A.Nimshan | 2025-01-01 | 2026-12-27 | Execution | 49% | 8% | Past due
P11A | Central Island master plan - Phase | Projects | A. Bumatia | 2023-01-01 | 2024-03-12 | Completed | 100% | 8% | Completed on t
P11B | Central Island master plan - Phase | Projects | A. Alsaif | 2025-02-01 | 2026-03-31 | Tendering | 9% | 8% | Past due
P11C | Central island Phase‑2 - Power and | Projects | M. Mahfouz | 2026-01-01 | 2026-12-31 | Execution | 23% | 8% | Past due
P11D | Central island Phase‑2 - Govt build | Projects | TBD | 2028-01-01 | 2028-01-01 | Not Started | 0% | 8% | Not started
P11E | Central island Phase‑2 - Cargo sepa | Projects | TBD | 2028-01-01 | 2028-01-01 | Not Started | 0% | 8% | Not started
P11F | Central island Phase‑2 - Procedure | Projects | TBD | 2028-01-01 | 2028-01-01 | Not Started | 0% | 8% | Not started
P11H | Central island Phase‑2 – Commercial | Projects | TBD | 2028-01-01 | 2028-01-01 | Not Started | 0% | 8% | Not started
P12 | KSA remote island master plan | Projects | A. Alsaif | 2025-01-01 | 2026-07-09 | Tendering | 7% | 8% | Past due
... +6 more |  |  |  |  |  |  |  |  | 
KFCA Seed Data (Pillars & Enablers) · Page 3

## Slide 4
ENABLER
Branding and social contribution — 4 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P75 | Brand marketing and social media pr | CX and Commercia | S. Marzooq | 2023-11-01 | 2025-01-07 | Completed | 100% | 100% | Completed on t
P76 | ESG strategy development and execut | Strategy and Ena | B. Alturki | 2024-02-05 | 2025-09-08 | Completed | 100% | 60% | Completed on t
P77 | Universal Accessibility Guidelines | Projects | H.Hamed | 2025-06-07 | 2026-05-07 | Execution | 16% | 40% | Past due
E6 | Women empowerment | CX and Commercia | TBD | 2026-05-01 | 2027-01-01 | Not Started | 0% | 10% | Not started
KFCA Seed Data (Pillars & Enablers) · Page 4

## Slide 5
ENABLER
Capability building — 9 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P65 | Intranet system engagement | CX and Commercia | S. Marzooq | 2024-12-01 | 2025-12-29 | Execution | 62% | 50% | Past due
P66 | Employee/organizational health inde | Shared Services | TBD | 2026-05-01 | 2026-12-01 | Not Started | 0% | 50% | Not started
P67 | Yearly training plans linked to com | Shared Services | O. Al-Shubli | 2025-04-01 | 2026-01-30 | Completed | 100% | 15% | Completed on t
P68 | Revised employee value proposition | Shared Services | TBD | 2027-03-01 | 2027-03-01 | Not Started | 0% | 15% | Not started
P69 | Clear career development paths | Shared Services | TBD | 2026-11-01 | 2027-08-01 | Not Started | 0% | 15% | Not started
P71 | Inclusion and diversity efforts | Shared Services | O. Al-Shubli | 2025-07-07 | 2026-06-30 | Execution | 24% | 10% | Past due
P72 | University partnerships to attract | Shared Services | TBD | 2026-08-01 | 2027-05-01 | Not Started | 0% | 15% | Not started
P73 | Global/regional operator exchanges | Strategy and Ena | T. Mofarrij | 2024-07-01 | 2026-06-12 | Execution | 45% | 10% | Past due
E5 | Leadership development program | Shared services | TBD | 2026-05-01 | 2026-08-01 | Not Started | 0% | 10% | Not started
KFCA Seed Data (Pillars & Enablers) · Page 5

## Slide 6
PILLAR
Commercialization — 10 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P25 | Dynamic pricing | Strategy and Ena | TBD | 2029-01-01 | 2029-01-01 | Not Started | 0% | 30% | Not started
P27 | Tolling packages | CX and Commercia | S. Marzooq | 2024-02-01 | 2024-02-01 | Not Started | 0% | 30% | Not started
P28 | Digital payments incentivization | CX and Commercia | T. Mofarrij | 2024-04-02 | 2025-12-13 | Completed | 100% | 40% | Completed with
P30 | Data monetization | Strategy and Ena | TBD | 2026-04-01 | 2028-06-01 | Not Started | 0% | 20% | Not started
P31 | Conservative comm. offerings expans | CX and Commercia | A. Alrayes | 2023-04-02 | 2024-04-11 | Completed | 100% | 13% | Completed with
P32 | Central island commercial developme | CX and Commercia | TBD | 2026-07-01 | 2026-07-01 | Not Started | 0% | 30% | Not started
P33A | Digital advertising (physical board | CX and Commercia | T. Mofarrij | 2024-12-01 | 2025-12-16 | Completed | 100% | 13% | Completed on t
P34 | Bonded zone/SEZ feasibility study | CX and Commercia | TBD | 2027-02-01 | 2027-02-01 | Not Started | 0% | 13% | Not started
P35 | Investment optimization | Finance | A. Almaghlou | 2024-07-03 | 2025-01-30 | Completed | 100% | 100% | Completed on t
P80 | Commercial B2B program study | CX and Commercia | T. Mofarrij | 2024-07-01 | 2024-07-01 | On Hold | 24% | 13% | On Hold
KFCA Seed Data (Pillars & Enablers) · Page 6

## Slide 7
PILLAR
Customer Experience — 8 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P19 | Trusted traveler program | Operations and M | A. Al Shrhan | 2027-02-01 | 2027-02-01 | On Hold | 0% | 33% | On Hold
P20 | Fast lane construction & optimizati | Operations and M | O. Aldahash | 2023-12-01 | 2024-07-29 | Completed | 100% | 33% | Completed with
P21 | Customer journey optimization | Operations and M | T. Mofarrij | 2024-01-04 | 2026-11-30 | Execution | 64% | 20% | Past due
P22 | Customer journey mapping & optimiza | Operations and M | M. Fattah | 2023-10-15 | 2024-02-15 | Completed | 100% | 20% | Completed with
P23A | Customer care centralization | CX and Commercia | B. AlTurki | 2024-05-12 | 2025-07-31 | Completed | 100% | 20% | Completed with
P24 | Customer satisfaction survey optimi | CX and Commercia | S. Marzooq | 2024-04-01 | 2026-01-05 | Completed | 100% | 20% | Completed on t
P92 | Enhance CX & gauge customer sentime | Strategy and Ena | TBD | 2027-02-01 | 2027-02-01 | Not Started | 0% | 33% | Not started
P23B | Customer Care Centralization Phase | CX and Commercia | TBD | 2026-10-01 | 2026-10-01 | Not Started | 0% | 20% | Not started
KFCA Seed Data (Pillars & Enablers) · Page 7

## Slide 8
ENABLER
Governance and steering — 17 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P36 | Strategy communication plan | Strategy and Ena | T. Mofarrij | 2023-10-10 | 2025-02-28 | Completed | 100% | 100% | Completed on t
P37A | Revision of internal policies, proc | GRC and cybersec | A. Alhamrani | 2023-12-10 | 2025-09-30 | Completed | 100% | 20% | Completed with
P37B | Revision of internal policies, proc | GRC and cybersec | M. Alotaibi | 2024-12-01 | 2025-09-30 | Completed | 100% | 4% | Completed with
P38 | Organization structure revamp | Shared Services | N. Almutairi | 2023-06-15 | 2024-05-22 | Completed | 100% | 10% | Completed with
P39 | Strategy execution governance | Strategy and Ena | T. Mofarrij | 2023-08-01 | 2024-12-19 | Completed | 100% | 10% | Completed with
P40 | Organizational business continuity | GRC and cybersec | A. Alhamrani | 2026-10-01 | 2027-03-01 | Not Started | 0% | 6% | Not started
P41 | External governance model revamp | Operations and M | O. Aldahash | 2024-01-28 | 2025-07-17 | Completed | 100% | 50% | Completed on t
P42 | Revision of bilateral agreement | Legal | TBD | 2026-10-01 | 2026-10-01 | On Hold | 0% | 50% | On Hold
P82 | Enterprise Risk Management (ERM) | GRC and cybersec | M. Alotaibi | 2024-12-01 | 2025-12-18 | Completed | 100% | 5% | Completed on t
P83 | Enterprise Compliance Management | GRC and cybersec | TBD | 2026-10-01 | 2027-03-01 | Not Started | 0% | 6% | Not started
P85 | Achieve cyber security excellence | GRC and cybersec | A. Bazaid | 2025-03-01 | 2025-12-29 | Execution | 89% | 5% | Past due
P86 | Foster cybersecurity defense | GRC and cybersec | A. Bazaid | 2025-03-01 | 2025-12-29 | Closing | 98% | 5% | Past due
P87 | Establish robust cybersecurity resi | GRC and cybersec | A. Bazaid | 2025-01-01 | 2025-12-29 | Execution | 92% | 5% | Past due
P88 | Establish data management office | Strategy and Ena | L. Basri | 2024-05-02 | 2025-10-08 | Completed | 100% | 10% | Completed on t
P91 | Enhance DMO Compliance integration | Strategy and Ena | L. Basri | 2026-02-15 | 2027-12-01 | Tendering | 5% | 6% | Past due
E1 | Environmental Sustainability standa | Projects | A. Alsaif | 2026-03-01 | 2026-12-01 | Planning | 1% | 6% | Past due
... +1 more |  |  |  |  |  |  |  |  | 
KFCA Seed Data (Pillars & Enablers) · Page 8

## Slide 9
ENABLER
Operational excellence — 9 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P43 | Outsourcing contracts revision | Shared Services | TBD | 2026-08-01 | 2027-03-01 | Not Started | 0% | 33% | Not started
P44 | Financial controlling | Finance | A.AlQahtani | 2024-09-01 | 2025-07-17 | Completed | 100% | 33% | Completed on t
P45 | Incentive schemes to optimize on‑th | Strategy and Ena | T. Mofarrij | 2024-11-03 | 2026-01-30 | Completed | 100% | 20% | Completed on t
P46 | Traveler pre-registration (Pax) | Technology and D | A. Alghamdi | 2023-06-01 | 2023-06-01 | Completed | 100% | 30% | Completed on t
P47 | Pre-clearance support (Cargo) | Operations and M | M. Fattah | 2026-02-01 | 2026-02-01 | Not Started | 0% | 10% | Not started
P81A | Toll gate expansion KSA | Projects | A.Nimshan | 2025-02-01 | 2027-01-30 | Execution | 10% | 20% | Past due
P81B | Toll gate expansion BAH | Projects | TBD | 2028-01-01 | 2028-01-01 | Not Started | 0% | 10% | Not started
P84 | Fixed assets tagging | Finance | I. Aloujail | 2024-09-02 | 2025-07-17 | Completed | 100% | 33% | Completed on t
E7 | Supply Chain excellence in ESG | Shared services | TBD | 2026-09-01 | 2026-12-01 | Not Started | 0% | 10% | Not started
KFCA Seed Data (Pillars & Enablers) · Page 9

## Slide 10
ENABLER
Private sector participation and funding — 2 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P78 | Private Sector involvement opportun | CX and Commercia | TBD | 2026-11-01 | 2027-08-01 | Not Started | 0% | 100% | Not started
P79 | Corporatization readiness | Strategy and Ena | T. Mofarrij | 2026-10-01 | 2027-06-01 | Not Started | 0% | 100% | Not started
KFCA Seed Data (Pillars & Enablers) · Page 10

## Slide 11
ENABLER
Technology and innovation — 19 projects
# | Project | Dept | PM | Start | End | Phase | Prog | Wt | Status
P50A | TMS & real-time performance dashboa | Technology and D | A. Alghamdi | 2023-12-01 | 2024-04-30 | Completed | 100% | 20% | Completed on t
P50B | TMS & real-time performance monitor | Technology and D | M. Albutery | 2025-03-20 | 2028-11-16 | Tendering | 9% | 20% | Past due
P51 | Staffing deployment linked to TMS | Operations and M | TBD | 2027-04-01 | 2027-04-01 | Not Started | 0% | 20% | Not started
P52 | Dynamic messaging | Technology and D | TBD | 2026-10-01 | 2027-09-01 | Not Started | 0% | 20% | Not started
P53 | Digital innovation hub | Technology and D | M. Albutery | 2027-01-01 | 2027-09-01 | On Hold | 0% | 20% | On Hold
P54 | Enhanced data analytics leveraging | Technology and D | R. Rushood | 2024-04-15 | 2025-11-08 | On Hold | 45% | 50% | On Hold
P55 | Digital crossings | Technology and D | TBD | 2027-01-01 | 2027-12-31 | Not Started | 0% | 33% | Not started
P56A | "One-stop shop" mobile app | Technology and D | A. Shareeda | 2023-06-01 | 2024-11-30 | Completed | 100% | 33% | Completed on t
P56B | JESR app revamp | Technology and D | T.Alrammah | 2026-04-01 | 2030-12-01 | Not Started | 0% | 33% | Not started
P58 | Digitization of internal processes | Technology and D | TBD | 2026-04-01 | 2027-03-01 | Not Started | 0% | 27% | Not started
P59 | ERP system enhancement | Technology and D | T.Alrammah | 2023-08-01 | 2025-07-17 | Completed | 100% | 20% | Completed on t
P60 | Optimize ITSM processes | Technology and D | A. Shareeda | 2026-03-01 | 2026-09-01 | Planning | 1% | 27% | Past due
P61 | Cybersecurity and data protection | GRC and cybersec | A. Bazaid | 2023-11-01 | 2027-07-12 | Execution | 66% | 25% | Past due
P62 | IT network infrastructure upgrade | Technology and D | TBD | 2026-06-01 | 2030-10-01 | Not Started | 0% | 25% | Not started
P63 | IT business continuity and Disaster | Technology and D | B. Alruwaili | 2024-03-03 | 2025-06-14 | Completed | 100% | 25% | Completed on t
P64 | Optimize data centers availability | Technology and D | B. Alruwaili | 2024-02-18 | 2025-07-17 | Completed | 100% | 25% | Completed on t
... +3 more |  |  |  |  |  |  |  |  | 
KFCA Seed Data (Pillars & Enablers) · Page 11

## Slide 12
Replit: Pillar vs Enabler Implementation
DATABASE CHANGE:
ALTER TABLE spmo_pillars ADD COLUMN IF NOT EXISTS pillar_type TEXT DEFAULT 'pillar';
-- CHECK (pillar_type IN ('pillar', 'enabler'))
DRIZZLE SCHEMA UPDATE:
In spmo.ts, add to spmoPillarsTable:
pillarType: text('pillar_type', { enum: ['pillar', 'enabler'] }).notNull().default('pillar'),
UI CHANGES:
1. Dashboard: Group 'Strategic Pillars' (3) separately from 'Enablers' (6) with section headers
2. Strategy Map: Show pillars as primary columns with enablers as supporting row below
3. Pillars page: Add a type badge ('PILLAR' blue / 'ENABLER' amber) next to each name
4. Sidebar: 'Pillars' link renamed to 'Pillars & Enablers' or keep as is with grouping inside
5. Executive PDF/PPTX reports: Show pillars first, enablers second with clear labels
COMPUTATION ENGINE: NO CHANGES
calcProgress, computeStatus, computeInitiativeStatus all work identically for both.
Strategy progress = simple average across all 9 (pillars + enablers) — same as before.
The only difference is visual grouping and labelling.
SEED DATA FILES:
• KFCA-SEED-DATA.ts — pillarsAndEnablers array with pillarType field
• KFCA-KPI-SEED-DATA.ts — KPIs reference pillar names (resolve to ID same way)
• Both files use the same pillar names — just add pillar_type on insert
KFCA Seed Data (Pillars & Enablers) · Page 12