## Slide 1
KFCA Corporate Strategy
Complete Seed Data for StrategyPMO
Sources: Strategy PDF (Nov 2025) + Project Tracker Excel (Mar 2026)
100 Projects · 26 Initiatives · 9 Pillars · 10 Departments
965 Milestones with Weights · Project & Initiative Weights Included
Budget Data · Risk Register · Dependency Matrices

## Slide 2
Programme at a Glance
100
Total Projects
34
Completed
12
In Execution
19
Past Due
41
Not Started
5
On Hold
965
Milestones
10
Departments
Pillar Progress
Assets & Infrastructure
25%
Customer Experience
66%
Commercialization
23%
Governance & Steering
69%
Operational Excellence
55%
Technology & Innovation
33%
Capability Building
25%
Branding & Social
91%
PS Participation
0%
KFCA StrategyPMO Complete Seed Data · Page 2

## Slide 3
Department Portfolio Summary
Department | Total | Done | Exec | Not Started | Past Due
Technology and Digitalization | 17 | 8 | 0 | 5 | 2
Projects | 17 | 2 | 5 | 7 | 7
Strategy and Enablement | 16 | 5 | 1 | 8 | 3
CX and Commercial | 15 | 6 | 1 | 7 | 1
GRC and cybersecurity | 11 | 3 | 3 | 4 | 4
Shared Services | 11 | 2 | 1 | 8 | 1
Operations and Maintenance | 9 | 5 | 1 | 2 | 1
Finance | 3 | 3 | 0 | 0 | —
Legal | 1 | 0 | 0 | 0 | —
KFCA StrategyPMO Complete Seed Data · Page 3

## Slide 4
Assets and infrastructure (22 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P1 | Meet iRAP requirements | Operations and Mai | O. Aldahash | Completed | 100% | 25% | 10% | Completed on tim
P2 | Automated equipment coverage (CCTV) | Technology and Dig | B. Alruwaili | Completed | 100% | 25% | 10% | Completed on tim
P5 | Cargo journey optimization | Projects | A. Bumteia | Execution | 82% | 25% | 10% | Delayed
P6 | Road assessment technologies | Operations and Mai | F. Yusuf | Completed | 100% | 25% | 5% | Completed on tim
P7 | Road and Facility Asset Management Sys | Technology and Dig | M. Albutery | Completed | 100% | 60% | 10% | Completed with d
P9 | Traffic monitoring and forecasting | Strategy and Enabl | TBD | Not Started | 0% | 40% | 4% | Not started
P10A | Enhancement of terminals & access | Projects | M. Salmeen | Completed | 100% | 8% | 3% | Completed on tim
P10B | Enhancement of customer terminals & ac | Projects | A.Nimshan | Execution | 49% | 8% | 2% | Past due
P11A | Central Island master plan - Phase 1 e | Projects | A. Bumatia | Completed | 100% | 8% | 5% | Completed on tim
P11B | Central Island master plan - Phase 2 d | Projects | A. Alsaif | Tendering | 9% | 8% | 8% | Past due
P11C | Central island Phase‑2 - Power and inf | Projects | M. Mahfouz | Execution | 23% | 8% | 6% | Past due
P11D | Central island Phase‑2 - Govt building | Projects | TBD | Not Started | 0% | 8% | 6% | Not started
P11E | Central island Phase‑2 - Cargo separat | Projects | TBD | Not Started | 0% | 8% | 6% | Not started
P11F | Central island Phase‑2 - Procedure are | Projects | TBD | Not Started | 0% | 8% | 6% | Not started
P11H | Central island Phase‑2 – Commercial ar | Projects | TBD | Not Started | 0% | 8% | 6% | Not started
... +7 more |  |  |  |  |  |  |  | 
KFCA StrategyPMO Complete Seed Data · Page 4

## Slide 5
Branding and social contribution (4 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P75 | Brand marketing and social media prese | CX and Commercial | S. Marzooq | Completed | 100% | 100% | 7% | Completed on tim
P76 | ESG strategy development and execution | Strategy and Enabl | B. Alturki | Completed | 100% | 60% | 10% | Completed on tim
P77 | Universal Accessibility Guidelines | Projects | H.Hamed | Execution | 16% | 40% | 5% | Past due
E6 | Women empowerment | CX and Commercial | TBD | Not Started | 0% | 10% | 3% | Not started
KFCA StrategyPMO Complete Seed Data · Page 5

## Slide 6
Capability building (9 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P65 | Intranet system engagement | CX and Commercial | S. Marzooq | Execution | 62% | 50% | 13% | Past due
P66 | Employee/organizational health index | Shared Services | TBD | Not Started | 0% | 50% | 10% | Not started
P67 | Yearly training plans linked to compet | Shared Services | O. Al-Shubli | Completed | 100% | 15% | 15% | Completed on tim
P68 | Revised employee value proposition | Shared Services | TBD | Not Started | 0% | 15% | 10% | Not started
P69 | Clear career development paths | Shared Services | TBD | Not Started | 0% | 15% | 10% | Not started
P71 | Inclusion and diversity efforts | Shared Services | O. Al-Shubli | Execution | 24% | 10% | 10% | Past due
P72 | University partnerships to attract tal | Shared Services | TBD | Not Started | 0% | 15% | 10% | Not started
P73 | Global/regional operator exchanges | Strategy and Enabl | T. Mofarrij | Execution | 45% | 10% | 4% | Past due
E5 | Leadership development program | Shared services | TBD | Not Started | 0% | 10% | 3% | Not started
KFCA StrategyPMO Complete Seed Data · Page 6

## Slide 7
Commercialization (10 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P25 | Dynamic pricing | Strategy and Enabl | TBD | Not Started | 0% | 30% | 3% | Not started
P27 | Tolling packages | CX and Commercial | S. Marzooq | Not Started | 0% | 30% | 3% | Not started
P28 | Digital payments incentivization | CX and Commercial | T. Mofarrij | Completed | 100% | 40% | 7% | Completed with d
P30 | Data monetization | Strategy and Enabl | TBD | Not Started | 0% | 20% | 4% | Not started
P31 | Conservative comm. offerings expansion | CX and Commercial | A. Alrayes | Completed | 100% | 13% | 7% | Completed with d
P32 | Central island commercial development | CX and Commercial | TBD | Not Started | 0% | 30% | 8% | Not started
P33A | Digital advertising (physical board) | CX and Commercial | T. Mofarrij | Completed | 100% | 13% | 5% | Completed on tim
P34 | Bonded zone/SEZ feasibility study | CX and Commercial | TBD | Not Started | 0% | 13% | 8% | Not started
P35 | Investment optimization | Finance | A. Almaghlou | Completed | 100% | 100% | 40% | Completed on tim
P80 | Commercial B2B program study | CX and Commercial | T. Mofarrij | On Hold | 24% | 13% | 9% | On Hold
KFCA StrategyPMO Complete Seed Data · Page 7

## Slide 8
Customer Experience (8 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P19 | Trusted traveler program | Operations and Mai | A. Al Shrhan | On Hold | 0% | 33% | 4% | On Hold
P20 | Fast lane construction & optimization | Operations and Mai | O. Aldahash | Completed | 100% | 33% | 30% | Completed with d
P21 | Customer journey optimization | Operations and Mai | T. Mofarrij | Execution | 64% | 20% | 10% | Past due
P22 | Customer journey mapping & optimizatio | Operations and Mai | M. Fattah | Completed | 100% | 20% | 5% | Completed with d
P23A | Customer care centralization | CX and Commercial | B. AlTurki | Completed | 100% | 20% | 3% | Completed with d
P24 | Customer satisfaction survey optimizat | CX and Commercial | S. Marzooq | Completed | 100% | 20% | 10% | Completed on tim
P92 | Enhance CX & gauge customer sentiment | Strategy and Enabl | TBD | Not Started | 0% | 33% | 3% | Not started
P23B | Customer Care Centralization Phase 2: | CX and Commercial | TBD | Not Started | 0% | 20% | 8% | Not started
KFCA StrategyPMO Complete Seed Data · Page 8

## Slide 9
Governance and steering (17 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P36 | Strategy communication plan | Strategy and Enabl | T. Mofarrij | Completed | 100% | 100% | 10% | Completed on tim
P37A | Revision of internal policies, process | GRC and cybersecur | A. Alhamrani | Completed | 100% | 20% | 40% | Completed with d
P37B | Revision of internal policies, process | GRC and cybersecur | M. Alotaibi | Completed | 100% | 4% | 5% | Completed with d
P38 | Organization structure revamp | Shared Services | N. Almutairi | Completed | 100% | 10% | 15% | Completed with d
P39 | Strategy execution governance | Strategy and Enabl | T. Mofarrij | Completed | 100% | 10% | 15% | Completed with d
P40 | Organizational business continuity Man | GRC and cybersecur | A. Alhamrani | Not Started | 0% | 6% | 10% | Not started
P41 | External governance model revamp | Operations and Mai | O. Aldahash | Completed | 100% | 50% | 23% | Completed on tim
P42 | Revision of bilateral agreement | Legal | TBD | On Hold | 0% | 50% | 100% | On Hold
P82 | Enterprise Risk Management (ERM) | GRC and cybersecur | M. Alotaibi | Completed | 100% | 5% | 5% | Completed on tim
P83 | Enterprise Compliance Management | GRC and cybersecur | TBD | Not Started | 0% | 6% | 2% | Not started
P85 | Achieve cyber security excellence | GRC and cybersecur | A. Bazaid | Execution | 89% | 5% | 5% | Past due
P86 | Foster cybersecurity defense | GRC and cybersecur | A. Bazaid | Closing | 98% | 5% | 5% | Past due
P87 | Establish robust cybersecurity resilie | GRC and cybersecur | A. Bazaid | Execution | 92% | 5% | 5% | Past due
P88 | Establish data management office | Strategy and Enabl | L. Basri | Completed | 100% | 10% | 10% | Completed on tim
P91 | Enhance DMO Compliance integration & t | Strategy and Enabl | L. Basri | Tendering | 5% | 6% | 4% | Past due
... +2 more |  |  |  |  |  |  |  | 
KFCA StrategyPMO Complete Seed Data · Page 9

## Slide 10
Operational excellence (9 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P43 | Outsourcing contracts revision | Shared Services | TBD | Not Started | 0% | 33% | 10% | Not started
P44 | Financial controlling | Finance | A.AlQahtani | Completed | 100% | 33% | 40% | Completed on tim
P45 | Incentive schemes to optimize on‑the-g | Strategy and Enabl | T. Mofarrij | Completed | 100% | 20% | 15% | Completed on tim
P46 | Traveler pre-registration (Pax) | Technology and Dig | A. Alghamdi | Completed | 100% | 30% | 5% | Completed on tim
P47 | Pre-clearance support (Cargo) | Operations and Mai | M. Fattah | Not Started | 0% | 10% | 11% | Not started
P81A | Toll gate expansion KSA | Projects | A.Nimshan | Execution | 10% | 20% | 7% | Past due
P81B | Toll gate expansion BAH | Projects | TBD | Not Started | 0% | 10% | 6% | Not started
P84 | Fixed assets tagging | Finance | I. Aloujail | Completed | 100% | 33% | 20% | Completed on tim
E7 | Supply Chain excellence in ESG | Shared services | TBD | Not Started | 0% | 10% | 3% | Not started
KFCA StrategyPMO Complete Seed Data · Page 10

## Slide 11
Private sector participation and funding (2 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P78 | Private Sector involvement opportuniti | CX and Commercial | TBD | Not Started | 0% | 100% | 5% | Not started
P79 | Corporatization readiness | Strategy and Enabl | T. Mofarrij | Not Started | 0% | 100% | 3% | Not started
KFCA StrategyPMO Complete Seed Data · Page 11

## Slide 12
Technology and innovation (19 projects)
# | Project | Department | PM | Phase | Actual % | Init Wt | Dept Wt | Status
P50A | TMS & real-time performance dashboard | Technology and Dig | A. Alghamdi | Completed | 100% | 20% | 5% | Completed on tim
P50B | TMS & real-time performance monitoring | Technology and Dig | M. Albutery | Tendering | 9% | 20% | 10% | Past due
P51 | Staffing deployment linked to TMS | Operations and Mai | TBD | Not Started | 0% | 20% | 2% | Not started
P52 | Dynamic messaging | Technology and Dig | TBD | Not Started | 0% | 20% | 2% | Not started
P53 | Digital innovation hub | Technology and Dig | M. Albutery | On Hold | 0% | 20% | 2% | On Hold
P54 | Enhanced data analytics leveraging big | Technology and Dig | R. Rushood | On Hold | 45% | 50% | 10% | On Hold
P55 | Digital crossings | Technology and Dig | TBD | Not Started | 0% | 33% | 10% | Not started
P56A | "One-stop shop" mobile app | Technology and Dig | A. Shareeda | Completed | 100% | 33% | 5% | Completed on tim
P56B | JESR app revamp | Technology and Dig | T.Alrammah | Not Started | 0% | 33% | 5% | Not started
P58 | Digitization of internal processes | Technology and Dig | TBD | Not Started | 0% | 27% | 5% | Not started
P59 | ERP system enhancement | Technology and Dig | T.Alrammah | Completed | 100% | 20% | 5% | Completed on tim
P60 | Optimize ITSM processes | Technology and Dig | A. Shareeda | Planning | 1% | 27% | 5% | Past due
P61 | Cybersecurity and data protection | GRC and cybersecur | A. Bazaid | Execution | 66% | 25% | 20% | Past due
P62 | IT network infrastructure upgrade | Technology and Dig | TBD | Not Started | 0% | 25% | 2% | Not started
P63 | IT business continuity and Disaster Re | Technology and Dig | B. Alruwaili | Completed | 100% | 25% | 5% | Completed on tim
... +4 more |  |  |  |  |  |  |  | 
KFCA StrategyPMO Complete Seed Data · Page 12

## Slide 13
Milestone/Activity Weights — Sample Projects
965 milestones extracted from 9 department sheets. Each has a weight (%) that sums to 100% per project. These map to spmo_milestones.weight in the tool.
P5: 35 activities, total weight: 100%
Phase | Activity | Wt | Prog
Planning | Produce site inspection report a | 2% | 0%
Planning | Develop concept design and area | 2% | 0%
Planning | Prepare RFP draft | 1% | 0%
Planning | Receive RFP approval | 1% | 0%
Tendering | Release RFP | 1% | 0%
Tendering | Receive bidders' proposals | 1% | 0%
Tendering | Evaluate bidders' proposals | 1% | 0%
Tendering | Award best bidder and sign contr | 2% | 0%
Execution | Phase 0 - Mobilization & site pr | 0% | 0%
Execution | Phase 1 - Demolishing and Remova | 1% | 0%
Execution | Phase 1 - New Custom Building | 2% | 0%
Execution | Phase 1 - New Storage Building | 3% | 0%
Execution | Phase 1 - Loading Dock | 8% | 0%
Execution | Phase 1 - Precast Boundary Wall | 0% | 0%
+21 more |  |  | 
P85: 10 activities, total weight: 100%
Phase | Activity | Wt | Prog
Planning | Define project scope | 2% | 0%
Planning | Create RFP | 3% | 0%
Tendering | Provide vendor list | 2% | 0%
Tendering | Identify awarded vendor | 3% | 0%
Execution | Upgrade/renewal SOC with monitor | 40% | 0%
Execution | Initiate innovation pilot projec | 25% | 0%
Execution | Trained SOC personnel on new too | — | 0%
Execution | Real-time dashboards and analyti | 20% | 0%
Closing | Submit final milestone | 3% | 0%
Closing | Submit closure and final sign-of | 2% | 0%
KFCA StrategyPMO Complete Seed Data · Page 13

## Slide 14
Data Model Mapping & Replit Instructions
Source Data | → Tool Entity | Count | Key Fields
Pillars + Enablers | spmo_pillars | 9 | name, color, weight, sortOrder
Initiatives (I-01 → I-26) | spmo_initiatives | 26 | pillarId, code, name, dates, budget
Projects (P1–P93 + E1–E8) | spmo_projects | 100 | initiativeId, deptId, PM, dates, budget, budgetSpent, weight (initiative_weight)
Activities (dept sheets) | spmo_milestones | 965 | projectId, name, phase, weight, effortDays, progress, responsible, dates
Project initiative_weight | project.weight | 100 | Determines how much a project contributes to its initiative's progress
Activity weight (%) | milestone.weight | 957 | Sum to 100% per project. Determines milestone contribution to project progress.
Departments (10) | spmo_departments | 10 | Tech, Strategy, CX, GRC, Ops, Projects, Finance, Services, Legal, Shared
Risks (RR_Backlog) | spmo_risks | ~2100 | riskId, project, description, likelihood, impact, level, mitigation
Dependencies (4.x sheets) | spmo_dependencies | ~50+ | Initiative S/D matrix + Project S/D matrix
CRITICAL WEIGHT MAPPING:
• project.weight = initiative_weight from Projects List col 16 (how much project counts toward initiative)
• milestone.weight = activity weight from dept sheets col 14 (how much milestone counts toward project)
• The calcProgress engine uses these weights: milestone→project (milestone.weight), project→initiative (project.weight as budget proxy)
KFCA StrategyPMO Complete Seed Data · Page 14